## RiskSerializationData8 (hidden)
Written By Version | 8.1.1
Serialization Major Version | 4
Serialization Minor Version | 0
Browse Record | Display Mode | Sens Graph Type | Cond Sens Settings | Scenario Settings | Selected Scenario | Distribution Options | Distribution GS | Distribution Curves | Sens Tornado Options | Sens Tornado GS | Sens Tornado Curves | Scen Tornado Options | Scen Tornado GS | Scen Tornado Curves | Sens Spider Option | Sens Spider GS | Sens Spider Curves
#NAME? | 0 | 5 | 4,10,2,.95,5,16,FALSE,0,TRUE,TRUE,TRUE |  | 0 | [6 empty] | 2;TRUE,.75,1 | GF1_4VKXXwEAEwBVAQwjACcANQB3AIUAhgCmALQAAAAAAE0BKAD//wAAAQEEAAAAAAMwLjAAAAABCER1cmF0aW9uATRTaWduaWZpY2FuY2Ugb2YgS2V5IElucHV0cyBXaGVyZSA3NSUgPCBPdXRwdXQgPCAxMDAlAQEKAAIAAQROb25lAwABAP8BAQEBARJJbnB1dCBTaWduaWZpY2FuY2UBAQEABAAAAAEBAQEBAAEBAQAEAAAACtMACOoACPUACAABCAsBCBYBCCEBCCwBCDcBCEIBCBUACER1cmF0aW9uAAAA/9wUPAEAAAIACQAAAAElAQAAAgAJAAAAAk8BAAACAAkAAAADjAEAAAIACQAAAARMAQAAAgAJAAAABTkBAAACAAkAAAAGTgEAAAIACQAAAAcjAQAAAgAJAAAACCkBAAACAAkAAAAJYAEAAAIABQABAQEAAAE= | #NAME?

## Sheet1
Kayson, The EPC Company
| Duration reduction factor | 0.25
| Duration increase factor | 0.6
| Stage | Weeks
|  | Min | Most Likely | Max | Actual (random) Duration
| Design | 21 | 28 | 44.8 | 28.0729
| Plan | 3.75 | 5 | 8 | 4.6808
| Digging | 4.5 | 6 | 9.6 | 6.3269
| Archaeological excavation | 3 | 4 | 6.4 | 4.1611
| Foundations | 7.5 | 10 | 16 | 15.0884
| Walls | 18 | 24 | 38.4 | 20.3958
| Roof | 3 | 4 | 6.4 | 4.9444
| Finishes | 9 | 12 | 19.2 | 11.749
| Installations | 3 | 4 | 6.4 | 5.5216
| Project Commissioning | 11.25 | 15 | 24 | 17.0608
| Finish Time | 84 | 112 | 179.2 | 118.0016